## Sheet1
SL | Date | Md. Rajibul Hasan | Md Fahad Hossain | Rahatul Islam | Munna
1 | 2021-03-08 | Ehsan Marketing Shopping Cart and Review | Boilerplate Creation, Login API, Refresh API, Feasibility Study, Research | EM-
2 | 2021-04-08 | Ehsan Marketing Shopping Cart and Review | JWT Authetication, UserInfo API, Documentation | EM | Redux store setup and , demo login
3 | 2021-05-08 | EM- Product Review | ProfileUpdate API, User IP Access, Location Access using Database, Location Access using Third Party API, FInally Documentation | EM | About page design of user profile
4 | 2021-07-08 | EM- Reg Form Validation | Metrimony Profile Table POST and GET API creation and documentation, Expectation ProfileTable, POST and GET api creation and Documentation | Understanding the responsibilities, Made roadmap on note. | User informantion and private route
5 | 2021-08-08 | WESS React Documentation Study ¦ EM- | Create Several Model, Serializers and API for Jobcategory,Special skills, jobprofile, Disability_info, Education_profile and then finally documentation of these API | Initialized Project and made jobProfile form (incomplete) | Multi step marriage profile edit form design
6 | 2021-09-08 | WESS React Documentation and Shared Component creation | Create model and API for Training,Experience, Project_works,SKills, Certificate model and documentation of API and insert 166Data to Special skills table |  | User profile complete login and redirect after login
7 | 2021-10-08 |  | Update,Delete,Detail API for some model , create model and serializer for reference and employer model and All related API for these Model and finally Documentation.